## Statistics (2)
Date | Cumulative Man-Hours worked | Number of Man Hours Worked | Number of Reportable Fatal Accident | Number of Reportable Non-Fatal Accident | Number of Dangerous Occurrences | Average Number of Personnel Daily i. Staff | ii. Worker includes sub-contractor:
2019-12-30 | 7000 | 7000 | 0 | 0 | 1 | 10 | 25
2020-01-01 | 15935 | 8935 | 0 | 0 | 2 | 12 | 25
2020-02-01 | 30040 | 14105 | 0 | 0 | 0 | 12 | 71
2020-03-01 | 47304 | 17264 | 0 | 0 | 0 | 12 | 71
2020-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2020-05-01 | 49504 | 2200 | 0 | 1 | 2 | 3 | 8
2020-06-01 | 52624 | 3120 | 0 | 0 | 0 | 7 | 8
2020-07-01 | 57808 | 5184 | 0 | 0 | 0 | 9 | 15
2020-08-01 | 68408 | 10600 | 0 | 1 | 1 | 13 | 40
2020-09-01 | 83800 | 15392 | 0 | 0 | 0 | 14 | 60
2020-10-01 | 103200 | 19400 | 0 | 0 | 0 | 13 | 82
2020-11-01 | 117152 | 13952 | 0 | 1 | 1 | 17 | 60
2020-12-01 | 133376 | 16224 | 0 | 1 | 1 | 18 | 60
2021-01-01 | 149576 | 16200 | 0 | 2 | 3 | 22 | 59
2021-02-01 | 161864 | 12288 | 0 | 0 | 1 | 22 | 42
2021-03-01 | 182040 | 20176 | 0 | 1 | 2 | 22 | 75
2021-04-01 | 205336 | 23296 | 0 | 0 | 0 | 22 | 90
2021-05-01 | 222392 | 17056 | 0 | 0 | 0 | 22 | 60
2021-06-01 | 239032 | 16640 | 0 | 0 | 0 | 20 | 60
2021-07-01 | 255880 | 16848 | 0 | 1 | 1 | 22 | 80
2021-08-01 | 277096 | 21216 | 0 | 1 | 1 | 22 | 80
2021-09-01 | 299693 | 22597 | 0 | 0 | 0 | 22 | 91
2021-10-01 | 312693 | 13000 | 0 | 0 | 0 | 22 | 21
2021-11-01 | 322677 | 9984 | 0 | 0 | 0 | 22 | 30
2021-12-01 | 336197 | 13520 | 0 | 0 | 0 | 22 | 30
2022-01-01 | 353797 | 17600 | 0 | 0 | 0 | 17 | 54

## Statistics
Sr. No. | Accident Statistics Summary | 2019-12-30 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01
1 | Number of Man-Hours worked | 7000 | 15935 | 30040 | 47304 | 0 | 49504 | 52624 | 57808 | 68408 | 83800 | 103200 | 117152 | 133376 | 149576 | 161864 | 182040 | 205336 | 222392 | 239032 | 255880 | 277096 | 299693 | 312693 | 322677 | 336197 | 353797
2 | Number of Man-Days worked | 875 | 1992 | 3755 | 5913 | 0 | 6188 | 6578 | 7226 | 8551 | 10475 | 12900 | 14644 | 16672 | 18697 | 20233 | 22755 | 25667 | 27790 | 29870 | 31976 | 34628 | 37425 | 39050 | 40298 | 51114 | 53314
3 | Number of Reportable Fatal Accident | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Number of Reportable Non-Fatal Accident | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
5 | Number of Dangerous Occurrences | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
6 | Number of Man-hours lost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1336 | 1336 | 1336 | 1336 | 1336 | 1336 | 1336 | 1336 | 1336 | 1336 | 1336 | 1336 | 1336 | 1336 | 1336
7 | Number of Man days lost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167 | 167
8 | Frequency Rate (LTIFR) - Number of Reportable Lost Time Injuries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.85 | 0.74 | 0.66 | 0.61 | 0.54 | 0.48 | 0.44 | 0.41 | 0.39 | 0.36 | 0.33 | 0.31 | 0.3 | 0.297 | 0.282
9 | Severity Rate (SR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142.54 | 125.2 | 111.64 | 103.17 | 91.73 | 81.33 | 75.09 | 69.8 | 65.2 | 60.26 | 55.72 | 53.4 | 51.75 | 49.46 | 47.2
10 | Incident Rate (IR) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 1.69 | 1.49 | 1.33 | 1.23 | 1.1 | 0.97 | 0.9 | 0.84 | 0.8 | 0.74 | 0.67 | 0.64 | 0.62 | 0.594 | 0.561
11 | Average Number of Personnel Daily i. Staff | 10 | 12 | 12 | 12 | 0 | 3 | 7 | 9 | 13 | 14 | 13 | 17 | 18 | 22 | 22 | 22 | 22 | 22 | 20 | 22 | 22 | 22 | 22 | 22 | 22 | 17
| ii. Worker includes sub-contractor: | 25 | 25 | 71 | 71 | 0 | 8 | 8 | 15 | 40 | 60 | 82 | 60 | 60 | 59 | 42 | 75 | 90 | 60 | 60 | 80 | 80 | 91 | 21 | 30 | 30 | 54
| Total | 35 | 37 | 83 | 83 | 0 | 11 | 15 | 24 | 53 | 74 | 97 | 77 | 78 | 81 | 64 | 97 | 112 | 82 | 80 | 81 | 102 | 113 | 43 | 52 | 52 | 71
(((3)+(4))/((1)))×100000
("Total Nos. of Mandays Lost" /"Total Man hours Worked" )×100,000
("Total no. of Accidents" /"Total no of persons employed" ) ×1000

## Site Accident
DELHI METRO RAIL CORPORATION LIMITED
Mumbai Line-2A Site accident matrix
Sl.No | Accident No. | Contract | Date of Incident | Day of incident | Time of incident | Brief Descripation of Incident | Type of incident (Fatal/Major/Dangerous Occurrence) | Cause of incident | Sub-Contractor | Public injury detail if any | Name of injured person | Gender of the injured | Age of the Injured | Occupation | Exact location of incident | Extent of injury/ Property Damage | Mandays Lost | Durations of work Stopped | Root Cause of the incident | Recommendations/Corrective action | Corrective action status | Reportable/Non-reportable | Hyperlink
1 | 1 | AE02R-1 | 2020-11-13 | Friday | 05:00pm | On 13 November 2020 approx 5;00pm One of the employee of M/s Chowdhary construction, who is carrying out OHE Execution activities of installation of dropper at Ramp area in Charkop depot using rail ladder trolly as per method statement, while moving the ladder trolly to next dropper location after completing previous dropper location, the technician Samirul Islam aged 23 years of Chowdhary Construction,who was on the ladder trolly, the ladder trolly got derailed due to improper welding on track joints and it cleand on the side and and individual fallen from height approximately 3/4 mtrs resulting some injuries on his face and stomach,the individualnot fasted his full body harness at time of movement of trolly. | Major | Due to fall from Rail track ladder Ladder | M/s Choudhary constructions | Yes | Samirul Islam | Male | 23 | Tecnician fitter | area | Face & stomach | 2 | 12 | 1.Incomplete 2.Negligence of work area feasibility 3.Movement of trolly with worker on board | 1.Counseling and briefing of risk analyasis about the incident happened on 13th Nov 2020. 2.Work area Feasibility check before commencement. 3.Indetification of risk related hazards before commencement. 4.No workmen on the ladder trolley during movement. But it required movement of trolley during dropping work,however we will ensure that during movement it will clamp on contact wire or person will come down. 5.Do not climb or alight unless trolley is on stationery position. 6.Fasting of safety harness during climbing up/down and while working. 7.During trolley movement our safety person will always available. ` | Corrective actions Implemented | Reportable | SA-01:DO-01
2 | 2 | AE02R-1 | 2021-09-23 | Thursday | 10:15am | On dated 23.09.2021 at around 10:15hrs Mr.Bhuvneshwar Sharma (assigned for the isolator of 25kV OHE of the particular Section) of SWPL was installing the discharge the rod Near SS-124 isolator,ETU building side at Down line following regular sequence of work as communicated by traction teams of DMRC over telephone & whatsapp confirming the location & position of isolators.while applying the discharge rod on contact wire of OHE ,a flash over occurred due to the portion where he was instructed by Coordinator of DMRC to position the discharge rod remained in charged condition. the impact force of flash over resulted in disbalance of the insulted discharge rod in his right hand due to which minor injury occurred to his right forearm. The victim immediately evacyated himself from the spot towards the Ramp area side and saw Mr.Aditya Kumar (DMRC) and Mr.Amit Kumar (SWPL) who were approaching towards the spot from ETU building side. After explaning the complete situation,Mr.Bhuvaneshwar Sharma was escorted to the ASS room by Mr.Aditya Kumar (DMRC) & Mr.Amit Kumar (SWPL) and Mr.Amit Kumar reported regarding the occurance to concerned staff of SWPL. During physical inspection & discussion with the victim we observed the victim to be normal with no major injury as the victim was wearing adequate personal protective equipments.the victim was immeadiately shifted to Yashasvi Hospital to evaluate his health condition & to provide medical treatment.Routine medical check-up were conducted and no major as confirmed by the on duty doctor.medical check-up were conducted and no major issues as confirmed by the doctor. the victim has been discharged from hospital after treatment and has undergone various medical check-up to ensure 100%recovery & fitness. the fitness certificate has been issued by the doctor. the victim has resumed his duties from 24th Sep 2021. | Dangerous Occurrence | Mis- communication | M/s Sterling & wilson O&M | Yes | Bhuvaneshwar Sharma | Male | 34 | ASS Operator | Near SS-124,ETU building side,Down main line | Minor Bruise Right forearm | Nil | 1Hrs | 1.Lack of understanding of electrical isolating points by the person engaged in commanding the switching operation is one of the probable causes where in the section of OHE presumed to be isolated remained in charged condition. 2.Standing instruction s for sequential switching operation while issuance of Power blocks to different stake holders not available with the switching operation team. 3.Absence of supervisory staff and written communication for shutdown operations not maintained. | 1.Training imparted on procedure to apply discharged rod. 2.Incident location visited by HSE Head of SWPL for investigation.Process innitiated for procurement of induction tester and voltage detector. | Corrective actions Implemented | Reportable | SA-02:MI-01
3 | 3 | AE02R-1 | 2021-11-28 | Sunday | 9:30pm | On 28th Nov,2021 at around 21:30Hrs, one of the employee Mr.Suraj Vasudev Dhumak of M/s VKAD Engineering who was appointed on the role ASS Mannning deputed at IC Colony Metro Station the Victim was coming Down from the under construction after completing their duty hours to give charge to other manning staff. But victim was connecting the concourse platform to Road Level,sand was spread in scattered manner over the steps due to which the foot sppiled on the steps resulted in loosing balance & fell down on the ground level the intermediate landing which as 6mtr above the Road level. Immediately the individual was rushed to the nearest Shatabdi Hospital in causality ward for further investigation & immediate medical assistance was made available. As a primary investigation the victim was undergone CT Scan following by X-Ray of Chest & foot. The X-Ray indicated about the multiple fractures on Right & Left leg, CT Scan observed to be normal as informed by duty doctor. The Victim emergency contact was made active and incident explained to his parents,accordingly father reported to hospital. Now the victim is undergoing further treatment at Shatabdi Hospital. | Major | 1.Unsafe staicase used. 2.No barricading provided to restriction of movement. 3.Sand scatters on the stairs by other construction agency. 4.Handrail not provied by civil agency. 5.The approach should be properly barricated to restrict the movement of workers. 6.Stairs are found to be accumulated with sand scatters. | VKAD | Yes | Suraj Dhumak | Male | 24 | ASS Operator | Metro Station Ic Colony | Injury | Nil | 4 Hrs | Unsafe staircase used | 1.Restriction to use incomplete stairs for movement. 2.Hard barricating for restriction of movement till completion of stairs construction. 3.Adequate illumination for temporary stairs arramgements. | Corrective actions Implemented | Reportable | SA-03:MI-02
5 | 5 | [21 empty] | SA-06:DO-04
[6 empty] | Minor | 0
[6 empty] | Major | 2
[6 empty] | Dangerous occurrence | 2
[6 empty] | Fatal | 0

## NCR
Mumbai Line-2A, AE02R-1 NCR matrix
NCR No. | Date | Description of Non conformity/ Observation | Clause Ref | Issued By | Received By | Responsibility | Closing Date
36
35
34
33
32
31
30
29
28
27
26
25
24
23
22
21
20
19
18
17
16
15
14
13
12
11
10
9
8
7
6
5
4
3
2
1

## Near Miss
DELHI METRO RAIL CORPORATION LIMITED
Mumbai Line-2A, Near Miss accident matrix
Accident No. | Contract | Date of Incident | Day of incident | Time of incident | Brief Descripation of Incident | Type of incident (Fatal/Major/Dangerous Occurrence) | Cause of incident | Sub-Contractor | Public injury detail if any | Name of injured person | Gender of the injured | Age of the Injured | Occupation | Exact location of incident | Extent of injury/ Property Damage | Mandays Lost | Durations of work Stopped | Root Cause of the incident | Recommendations/Corrective action | Corrective action status | Reportable/Non-reportable | Hyperlink
1 | AE02R-1 | 2020-12-28 | Monday | 10:37AM | On 28-Dec-20 labour while some labours of M/s Rahul Agencies was talking the rail mounted mobile scaffolding which was already rejected by pushing it, derailment has taken place.luckily there was no casualty. | Mechanical failure of wheel and outrigger | Use of rejected scaffolding | Rahul Agencies | Nil | Nil | NIL | Nil | Nil | Ramp area | NiL | NIL | Nil | Use of rejected scaffolding | Replaced the scaffolding | Replaced the scaffolding | Non-Reportable | SA-1:NM-1
2 | AE02R-1 | 2021-06-30 | Wednesday | 16:30 | On dated 30-06-2021 while of M/s Rahul Agencies Mr.Habidur Rahman was doing cantilever adjustment at location Anand Nagar to Dahisar ,Due to tension of contact wire at curve area,the contact wire hit the individual while adjusting, due to this the individual came out of trolley and protected by ssafety Harness, the ladder rolley is at stand still. As he was wearing safety harness which was anchored with contact wire the major incident was averted does not fall down and remain suspended in the air. | Dangerous Occurrence | Height of the contact wire from rail level is 5mtr while the trolley height is 4.7 mtr Due to this top railing was not available . Moreover worker standing in front of contact wire was in high tension get jerked. He may fell down on the track which lead to major injury or even demise of the person. | Rahul Agencies | Nil | Nil | NIL | Nil | Nil | Dahisar | Nil | NIL | 30 Min | 1.Poor planning 2.Poor supervision 3.From contact wire from rail level is 5mtr while the trolley height is approx 4.7mtr due to this top railing was not available. 5.Moreover worker standing in front of contact wire which was in high tension get jerked. | 1. More attention needed while doing such activities. 2. Only Trained Workmen should be deployed in doing such operations. 3. Work should be carried under Strict Supervision. 4.Railing should be provided at top of trolley. | Corrective actions Implemented | Non-Reportable | SA-06:NM-03
3 | AE02R-1 | 2021-11-17 | Wednesday | 12:35pm | On dated 17-11-2021 at 12:35pm Sharifuddin Islam Fitter of M/s Rahul Agencies was engaged for straightening of foundation bolt casted on top level of parapet wall for Mast erection at location 11/34 between Malad and Kasturi park Metro station. He was hammering at the projected part of the bolt to staighten it when that part of the bolt of size 28mm X114 mm approximately broke and fell on to the below traffic road from a height of arround 13.25mtrs without injuring any person. work executed without PTW. | Dangerous Occurrence | Catch net not provided | Rahul Agencies | NIL | Nil | NIL | NIL | Nil | Mast location no 11/34, between Malad & Kasturi Park staion | NIL | NIL | 30 Minutes | 1.Poor planning 2.Poor supervision Catch net not provided to prevent fall of materials from viaduct. | To install catch net at viaduct to prevent fall of materials. 1. More attention needed while doing such activities. 2. Only Trained Workmen should be deployed in doing such operations. 3. Work should be carried under Strict Supervision. | Corrective actions Implemented | Non-Reportable | SA-11:NM-04

## First Aid Register
STERLING AND WILSON PVT LTD Date:-03-07-2021
First Aid Register
SR.NO | DATE | WORKER NAME | AGE / SEX | NAME OF CONTRACTOR | Occupation | Injury Type | Part Injured | Activity perfomed | TREATMENT | INCIDENT LOCATION | PHOTOS | Recommendations
1 | 2021-07-30 | Nurul Hoque | 22/m | Rahul Agencies | Helper | Minor | Right hand small finger | BEC cable laying | Dressed & Bandaged | Dahisar on viaduct
2 | 2021-08-06 | kamrul Hoque | 24 | Rahul Agencies | Helper | Minor | Small cut on left hand finger from wire | Catenary wire | Dressed & Bandaged | Dahisar on viaduct
3 | 2021-08-27 | Sonu Yadav | 27 | Rahul Agencies | OHE-Fitter | Minor | Thurt at leg while climbing RRV | During the Cantilever | Fast Relief Spray | Borivali
4 | 2021-09-07 | Sharifuddin | 23 | Rahul Agencies | OHE-Fitter | Minor | Small cut on left hand finger from share edge | Cantiliver installation | Dressed & Bandaged | Ic Colony
5 | 2021-09-18 | Bani | 23 | Rahul Agencies | OHE-Fitter | Minor | Small cut on left leg climbing on staircase | Material shifting | Dressed & Bandaged | Kamraj Nagar
6 | 2021-10-06 | Sarit Sk | 23 | Rahul Agencies | Helper | Minor | Left hand small finger injury | Scaffoldiing shifting | Dressed & Bandaged | Kamraj Nagar
7 | 2021-10-15 | Patta Surjit | 25 | Rahul Agencies | Helper | Minor | Left leg toe injury due to defected safety shoes | Material shifting | Dressed & Bandaged | Depot
8 | 2021-10-21 | Mokim Seikh | 22 | Rahul Agencies | Helper | Minor | Thurt on left hand wrist | Mast Shifting | Dressed & Bandaged | Depot
9 | 2021-10-26 | Narendra Singh | 24 | Rahul Agencies | Helper | Minor | Small cut on right hand thumb | Derrick pole | Dressed & Bandaged | Mahavir Nagar
10 | 2021-12-26 | Santosh Kumar | 25 | Rahul Agencies | OHE-Fitter | Minor | Small cut on left hand knee | Cantilever Installation | Dressed & Bandaged | Eksar
11 | 2021-11-03 | Jiyat Ram | 27 | Rahul Agencies | OHE-Fitter | Minor | Injured on wrist left leg due to sharp edge. | Material shifting | Dressed & Bandaged | Anand Nagar
12 | 2021-11-19 | Saddam Hussain | 26 | Rahul Agencies | Asst-Fitter | Minor | Small cut on left hand palm from cantilever | Cantilever Installation | Dressed & Bandaged | Kamraj Nagar
13 | 2022-02-10 | Barkat Ali | 28 | Rahul Agencies | Asst-Fitter | Minor | Left leg injury due to sharp edge | Material shifting | Dressed & Bandaged | DN Nagar
14 | 2022-04-08 | Mehebub Alam | 23 | Rahul Agencies | Jr. Fitter | Minor | Small cut occurred in right hand while cutting the IPS tube | IPS tube cutting | Dressed & Bandaged | Depot
15 | 2022-06-18 | Sadikul Islam | 21 | Rahul Agencies | Helper | Minor | Rigght hand injury due to sharp edge | Mast shifting | Dressed & Bandaged | Oshiwara
16 | 2022-10-28 | Fotik Sekh | 26 | Rahul Agencies | Fitter | Minor | During cantiliver adjustment the thumb of the right hand got injured | Cantiliver installation | Dressed & Bandaged | Malad Station
17 | 2022-12-12 | Sadam Sekh | 27 | Rahul Agencies | Fitter | Minor | Right hand hurt while tightening nut bolt of mast pole | Nut bolt tightening | Dressed & Bandaged | Charkop Station
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68

## Quarterly audit details
DELHI METRO RAIL CPRORATION LIMITED
Mumbai Line-2A Quarterly SHE Audit
Audit No | Date of Audit | Contractor | Contract No. | Agency Name | N1 | N2 | Compliance Audit date | Status of N1 & N2 | Details of open NCRs | Pending Observations
1 | 1st Quarterly, 3rd & 5th Feb 2022 | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | ISDC | 6 | 8 | 21/02/2022 | NC- 08 complied (N1&N2) | N1-00 & N2-00 | NIL
2 | 2nd Quarterly 6th & 7th May,2022 | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | ISDC | 9 | 7 | 27/05/2022 | NC-07 complied (N1 & N2 ) | N1-00 & N2-00 | NIL
3 | 3rd Quartely 24 Aug to 25 Aug 2022 | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | ISDC | 8 | 6 | 2022-09-04 | NC-04 complied (N1 & N2 ) | N1-00 & N2-01 | NIL
4
5
6
7
8
9
10

## Safety walk
DELHI METRO RAIL CORPORATION LIMITED
MMRDA LINE,2A Weekly Safety walk Down
Inspection No | Date of inspection | Location | Contractor | Contract no | Participation of PM/DMRC | Participation of any other DMRC rep | Participation of Contractor PM | Observation Raised | Compliance | Remark if any
1 | 2021-11-09 |  | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM, Mr.Ganesh Arote | Mr.Shiv Prasad | 16 | 16
2 | 2021-09-17 |  | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Ganesh Arote,Mr.Hasruddin Ahmad | Mr.Pulkit Bhardwaj | 12 | 12
3 | 2021-09-23 |  | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Ganesh Arote,Mr.Hasruddin Ahmad,Mr.Abhishek Otta | Mr.Pulkit Bhardwaj | 14 | 14
4 | 2022-02-10 |  | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh,Mr.Hasruudin Ahmad | Mr.Pulkit Bhardwaj | 11 | 11
5 | 2022-02-23 |  | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh,Mr.Hasruudin Ahmad | Mr.Pulkit Bhardwaj | 13 | 13
6 | 2022-03-02 | Viaduct | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh,Mr.Hasruudin Ahmad | Mr.Pulkit Bhardwaj | 18 | 18
7 | 2022-03-15 | Viaduct | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh,Mr.Hasruudin Ahmad | Mr.Pulkit Bhardwaj | 16 | 16
8 | 2022-03-30 | Viaduct | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh,Mr.Hasruudin Ahmad | Mr.Pulkit Bhardwaj | 12 | 12
9 | 2022-04-08 | Viaduct | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh, Mr.Hasruudin Ahmad | Mr.Pulkit Bhardwaj | 12 | 12
10 | 2022-04-16 | Viaduct | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh, Mr.Hasruudin Ahmad | Mr.Pulkit Bhardwaj | 9 | 9
11 | 2022-04-28 | Viaduct | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh, Mr.Hasruudin Ahmad | Mr.Pulkit Bhardwaj | 7 | 7
12 | 2022-05-04 | Viaduct | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh, Mr.Hasruudin Ahmad | Mr.Pulkit Bhardwaj | 11 | 11
13 | 2022-05-19 | Viaduct | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh, Mr.Hasruudin Ahmad | Mr.Nitin Khandelwal | 8 | 8
14 | 2022-06-07 | Viaduct | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh, Mr.Hasruudin Ahmad | Mr.Nitin Khandelwal | 9 | 9
15 | 2022-06-25 | Viaduct | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh, Mr.Hasruudin Ahmad | Mr.Nitin Khandelwal | 11 | 11
16 | 2022-07-06 | Viaduct | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh, Mr.Hasruudin Ahmad | Mr.Nitin Khandelwal | 15 | 15
17 | 2022-07-26 | Viaduct | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh, Mr.Hasruudin Ahmad | Mr.Nitin Khandelwal | 14 | 14
18 | 2022-08-13 | Viaduct | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh, Mr.Hasruudin Ahmad | Mr.Nitin Khandelwal | 16 | 16
19 | 2022-08-23 | Viaduct | M/s Rahul Agencies | AE-02R1:Line,2A | No | Mr.Gurumel Singh, Mr.Hasruudin Ahmad | Mr.Nitin Khandelwal | 13 | 13
20 | 2022-09-05 | Depot | M/s Vkad | AE-02R1:Line,2A | No | Mr.Hasruddin Ahmad, Mr.Abhay Singh | Mr.Nitin Khandelwal | 2 | 1
21 | 2022-09-12 | Depot | M/s Vkad | AE-02R1:Line,2A | No | Mr.Hasruddin Ahmad, Mr.Abhay Singh | Mr.Nitin Khandelwal | 2
22 | 2022-09-22 | Depot | M/s Vkad | AE-02R1:Line,2A | No | Mr.Hasruddin Ahmad, Mr.Abhay Singh | Mr.Nitin Khandelwal | 2
23 | 2022-10-03 | Depot | M/s Vkad | AE-02R1:Line,2A | No | Mr.Hasruddin Ahmad, Mr.Abhay Singh | Mr.Nitin Khandelwal | 2 | 1
24 | 2022-10-10 | Depot | M/s Vkad | AE-02R1:Line,2A | No | Mr.Hasruddin Ahmad, Mr.Abhay Singh | Mr.Achinta Chowdhury Mr.Harish Mishra | 2
25 | 2022-10-17 | Depot | M/s Vkad | AE-02R1:Line,2A | No | Mr.Hasruddin Ahmad, Mr.Abhay Singh | Mr.Achinta Chowdhury | 2
26 | 2022-11-12 | Depot | M/s Vkad | AE-02R1:Line,2A | No | Mr.Hasruddin Ahmad, Mr.Gurumel Singh | Mr.Nitin Khandelwal | 2
27 | 2022-11-19 | Depot | S&W | AE-02R1:Line,2A | No | Mr.Hasruddin Ahmad, Mr.Abhay Singh | Mr.Achinta Chowdhury Mr.Harish Mishra | 2
28 | 2022-11-26 | Depot | M/s Vkad | AE-02R1:Line,2A | No | Mr.Hasruddin Ahmad, Mr.Gurumel Singh | Mr.Nitin Khandelwal | 2

## Safety Committee meeting
DELHI METRO RAIL CPRORATION LIMITED
Mumbai Line-2A, Monthly SHE committee meeting
Meeting No | Date of Meeting | Location | Contractor | Contract No. | Participation of PM/DMRC | Participation by any other DMRC rep | Participation of Contractor PM | Remarks if any
1 | 2019-12-21 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Francis john,Mr.Shiv Prasad,Mr.Pulkit Bhardwaj,Mr.Durgesh Rai,Mr.Kushwant Dave,Mr.Harish Mishra,Mr.R.Dhanapandi,Hasruddin Ahmad,Mr.Lalit Bhatt,Mr.Chinmay Palshetkar,Mr.Mansingh | Mr.Francis John
2 | 2020-01-13 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Francis john,Mr.Shiv Prasad,Mr.Pulkit Bhardwaj,Mr.Durgesh Rai,Mr.Kushwant Dave,Mr.Harish Mishra,Mr.R.Dhanapandi,Hasruddin Ahmad,Mr.Lalit Bhatt,Mr.Anindya Sundar Bera,Mr.Arbaj Ansari(Ved Ele),Mr.Sunil (Choudhary) | Mr.Francis John
3 | 15.02.2020 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Shiv Prasad,Mr.Hasruddin Ahmad,Mr.Lalit Bhatt,Mr.Dheeraj joshi(DMRC)Mr.Deepesh Deharia(DMRC)Mr.Sunil Kumar(Choudhary)Mr.Mansingh(Ved Ele)Mr.Somnath Abhale(Rahul)Mr.Anil Bhagmore(Rahul) | Mr.Francis John
4 | 02.03.2020 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM, Mr.Bonod Kushwaha, Mr.Hasruddin Ahmad,Francis John.Mr.Durgesh Rai,Mr.Shiv Prasad,Mr.R.Dhanapandi,Mr.Gurumel Singh,Mr.Vijay kumar Sharma(DMRC)Mr.Chinamay Palshetkar,Mr.Lalit Bhatt,Mr.Mansingh (Ved Ele)Mr.Sunil(Choudhary)Mr.Somnath Abhale(Rahul) | Mr.Francis John
5 | 29.06.2020 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM, Mr.Bonod Kushwaha, Mr.Hasruddin Ahmad,Francis John. Mr.Shiv Prasad | Mr.Francis John
6 | 27.07.2020 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM, Mr.Binod Kushwaha, Mr.Hasruddin Ahmad,Francis John. Mr.Shiv Prasad | Mr.Francis John
7 | 2022-08-10 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Vamshi Krishnan(DMRC)Mr.Mr.Dheeraj Joshi(DMRC)Mr.Navrang Saini9DMRC)Mr.Vijay Sharma(DMRC)Mr.RK Shahu(DMRC)Mr.Sachin Mishra(DMRC)Mr.Rupak Choudhary(DMRC)Mr.Bappaditya Mukherjee,Mr.Kumar Shailendra,Mr.Francis John,Mr.Anamitra Kalita,Mr.Harish Mishra
5 | 31.08.2020 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury (DMRC) Mr.Bonod Kushwaha, Mr.Hasruddin Ahmad,Francis John. Mr.Shiv Prasad | Mr.Francis John
6 | 2021-09-03 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Pavan Kumar(DMRC) Mr.Rupak Choudhary(DMRC)Mr.Navrang Saini(DMRC)Mr.Aditya(DMRC)Mr.Naveen Balan,mr.Anamitra Kalita,Mr.Vishnu Reddy(Skylark) | Mr.Naveen Balan
7 | 22.10.2020 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM, Mr.Bonod Kushwaha, Mr.Hasruddin Ahmad,Francis John. Mr.Shiv Prasad | Mr.Francis John
8
9 | 25.01.2021 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chodhury AM, Mr.Sushanta Bemal,Mr.Hasruddin Ahmad,Mr.Francis John,Mr.Shiv Prasad | Mr.Francis John
10 | 15.02.2021 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM, Mr.Sushanta Bemal,Mr.Hasruddin Ahmad,Mr.Francis John,Mr.Shiv Prasad | Mr.Francis John
11 | 02.03.2021 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM, Mr.Sushanta Bemal,Mr.Hasruddin Ahmad,Mr.Francis John,Mr.Shiv Prasad | Mr.Francis John
12 | 02.04.2021 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM, Mr.Sushanta Bemal,Mr.Hasruddin Ahmad,Mr.Francis John | Mr.Francis John
13 | 06.05.2021 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM, Mr.Sushanta Bemal,Mr.Hasruddin Ahmad,Mr.Francis John | Mr.Francis John
14 | 03.06.2021 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM, Mr.Sushanta Bemal,Mr.Hasruddin Ahmad,Mr.Francis John | Mr.Francis John
15 | 01.07.2021 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM, Mr.Sushanta Bemal,Mr.Hasruddin Ahmad,Mr.Francis John | Mr.Francis John
16 | 05.08.2021 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM,Mr.Anamitra Kalita,Mr.Francis John,Mr.Hasruddin Ahmad,Mr.Ganesh Arote,Mr.Pulkit Bhardwaj,Mr.Harish Mishra | Mr.Francis John
17 | 29.08.2021 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM,Mr.Anamitra Kalita,Mr.Francis John,Mr.Hasruddin Ahmad,Mr.Ganesh Arote,Mr.Pulkit Bhardwaj,Mr.Harish Mishra | Mr.Francis John
19 | 31.10.2021 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM,Mr.Anamitra Kalita,Mr.Francis John,Mr.Hasruddin Ahmad,Mr.Ganesh Arote,Mr.Pulkit Bhardwaj,Mr.Harish Mishra | Mr.Francis John
20 | 30.11.2021 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM,Mr.Anamitra Kalita,Mr.Francis John,Mr.Hasruddin Ahmad,Mr.Ganesh Arote,Mr.Pulkit Bhardwaj,Mr.Harish Mishra | Mr.Francis John
21 | 30.12.2021 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM,Mr.Anamitra Kalita,Mr.Francis John,Mr.Hasruddin Ahmad,Mr.Ganesh Arote,Mr.Pulkit Bhardwaj,Mr.Harish Mishra | Mr.Francis John
22 | 28.02.2022 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM,Mr.Anamitra Kalita,Mr.Francis John,Mr.Hasruddin Ahmad,Mr.Ganesh Arote,Mr.Pulkit Bhardwaj,Mr.Harish Mishra | Mr.Francis John
23 | 30.04.2022 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM,Mr.Hasruddin Ahmad mr.Ganesh Arote,Mr.Francis John,Mr.Harish Mishra | Mr.Francis John
24 | 04.05.2022 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM,Mr.Hasruddin Ahmad mr.Ganesh Arote,Mr.Francis John,Mr.Harish Mishra | Mr.Francis John
25 | 04.06.2022 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM,Mr.Hasruddin Ahmad mr.Ganesh Arote,Mr.Francis John,Mr.Harish Mishra | Mr.Francis John
26 | 2022-07-04 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM,Mr.Hasruddin Ahmad mr.Ganesh Arote,Mr.Francis John,Mr.Harish Mishra | Mr.Francis John
27 | 2022-08-08 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Rupak Chowdhury AM,Mr.Hasruddin Ahmad mr.Ganesh Arote,Mr.Francis John,Mr.Harish Mishra | Mr.Francis John
28 | 2022-11-21 | Depot | M/s Sterling & Wilson Pvt Ltd | AE-02R1:Line,2A | No | Mr.Achinta Chowdhury,Mr.Harish Mishra,Mr.Nitin Khandelwal,Mr.Hasruddin Ahmad,Mr.Gurumel Singh,Mr.Hemant Shawant | Mr.Achinta Chowdhury